## Foglio1
DATA | ORA INIZIO | TEMPO IMPIEGATO | N0ME PERSONA | PROGETTO | FASE | DISCIPLINA | ITERAZIONE | NOTE
2016-03-22 | 9:30 | 120 | Maria, Alfedo, Gabriele | Perfect Places | Inception | Requirements | 0 | Primo incontro e analisi del problema
2016-04-01 | 9:30 | 120 | Maria, Alfedo, Gabriele | Perfect Places | Inception | Requirements | 0 | Elicitazione requisiti
2016-04-02 | 9:30 | 120 | Maria, Alfedo, Gabriele | Perfect Places | Inception | Requirements | 0 | Elicitazione casi d'uso
2016-04-15 | 9:30 | 180 | Maria, Alfedo, Gabriele | Perfect Places | Inception | Requirements | 0 | Documento di Vision
2016-04-17 | 9:30 | 60 | Maria, Alfedo, Gabriele | Perfect Places | Inception | Requirements | 0 | Matrice tracciabilità
2016-04-26 | 9:30 | 180 | Maria, Alfedo, Gabriele | Perfect Places | Elaboration | Analysis and design | 1 | Use Case Diagrams
2016-05-03 | 9:30 | 120 | Maria, Alfedo, Gabriele | Perfect Places | Elaboration | Analysis and design | 1 | Activity Diagrams
2016-05-05 | 9:30 | 120 | Maria, Alfedo, Gabriele | Perfect Places | Elaboration | Analysis and design | 1 | Sequance Diagrams
2016-05-17 | 9:30 | 120 | Maria, Alfedo, Gabriele | Perfect Places | Elaboration | Analysis and design | 1 | Class Diagrams
2016-05-30 | 9:30 | 120 | Maria, Alfedo, Gabriele | Perfect Places | Construction | Implemetation | 2 | Model in Java, JSP, JS: Login, Logout
2016-06-02 | 9:30 | 120 | Maria, Alfedo, Gabriele | Perfect Places | Construction | Implemetation | 2 | Model in Java, JSP, JS: Registrazione
2016-06-05 | 9:30 | 120 | Maria, Alfedo, Gabriele | Perfect Places | Construction | Implemetation | 2 | Model in Java, JSP, JS: Gestione del Profilo Personale
2016-06-11 | 9:30 | 120 | Maria, Alfedo, Gabriele | Perfect Places | Construction | Implemetation | 2 | Model in Java, JSP, JS: Gestione Locazioni
2016-06-19 | 9:30 | 120 | Maria, Alfedo, Gabriele | Perfect Places | Construction | Implemetation | 2 | Model in Java, JSP, JS: Gestione Posta
2016-06-21 | 9:30 | 120 | Maria, Alfedo, Gabriele | Perfect Places | Construction | Implemetation | 2 | Model in Java, JSP, JS: Gestione Prenotazioni
2016-06-23 | 9:30 | 120 | Maria, Alfedo, Gabriele | Perfect Places | Construction | Implemetation | 2 | Model in Java, JSP, JS: Gestione Utenti
2016-06-26 | 9:30 | 120 | Maria, Alfedo, Gabriele | Perfect Places | Construction | Implemetation | 2 | Model in Java, JSP, JS: Ricerca Locazione
2016-06-29 | 9:30 | 120 | Maria, Alfedo, Gabriele | Perfect Places | Construction | Implemetation | 2 | Model in Java, JSP, JS: Visualizza Preventivo
2016-06-30 | 9:30 | 120 | Maria, Alfedo, Gabriele | Perfect Places | Construction | Implemetation | 2 | Model in Java, JSP, JS: Crea Amministratore
2016-07-01 | 9:30 | 120 | Maria, Alfedo, Gabriele | Perfect Places | Construction | Implemetation | 2 | Model in Java, JSP, JS: Gestione Lingua
2016-07-03 | 9:30 | 120 | Maria, Alfedo, Gabriele | Perfect Places | Construction | Implemetation | 2 | Model in Java, JSP, JS: Gestione FAQ
2016-08-04 | 9:30 | 60 | Maria, Alfedo, Gabriele | Perfect Places | Construction | Test | 3 | Testing
2016-08-05 | 9:30 | 60 | Maria, Alfedo, Gabriele | Perfect Places | Construction | Test | 3 | Testing
2016-08-07 | 9:30 | 60 | Maria, Alfedo, Gabriele | Perfect Places | Construction | Test | 3 | Testing
2016-08-08 | 9:30 | 60 | Maria, Alfedo, Gabriele | Perfect Places | Construction | Implemetation | 3 | Correzione codice a seguito di un bug
2016-08-09 | 9:30 | 60 | Maria, Alfedo, Gabriele | Perfect Places | Construction | Test | 3 | Testing
2016-08-10 | 9:30 | 60 | Maria, Alfedo, Gabriele | Perfect Places | Construction | Test | 3 | Testing
2016-08-12 | 9:30 | 60 | Maria, Alfedo, Gabriele | Perfect Places | Transition | Project Management | 4 | Incontro conclusivo
2017-02-13 | 9:30 | 120 | Maria, Alfedo, Gabriele | Perfect Places | Transition | Transition | 4 | Presentazione progetto